| Section | Actions | Leads | Success measures | Timescale / Notes | DfE area |
| --- | --- | --- | --- | --- | --- |
| 1. Staff expertise & culture | Learn together: All staff have a yearly session on saving energy, water, and caring for the planet. Site Manager: Learn how to read meters and spot simple problems. Energy Champions: Pick one staff member and one pupil leader. Daily Checklist: Each classroom checks lights, windows, and devices before leaving. Save Paper: Print double-sided and use digital homework. Reuse Station: A place for sharing and reusing supplies. | KA LR ND | Learn Together (Staff CPD) All staff attend one annual session on saving energy, water, and caring for the planet. Staff can explain at least three ways to save energy and water in school. Site Manager Training Site Manager completes training on reading meters and spotting simple faults within 6 months. Site Manager demonstrates ability to record meter readings and report issues accurately. Energy Champions One staff member and one pupil are appointed as Energy Champions. Champions lead at least one energy-saving activity or campaign each term. Daily Checklist Every classroom uses the checklist daily to check lights, windows, and devices before leaving. 90% compliance recorded in termly monitoring. Save Paper All printing is double-sided by default. At least 50% of homework is submitted digitally by the end of the year. Reuse Station A reuse station is set up and used by staff and pupils. At least 10 items reused or shared each term. | Immediate priority: CPD & checklist rollout term Site Manager training within 6 months. | Leadership & Management; Staff Development |
| 2. Buildings, grounds & resilience | Energy Check: Look at how much energy we use and find ways to save. Better Lighting: Use LED lights and sensors so lights turn off when not needed. Fix Leaks: Stop roof leaks and draughts. Heating: Fit radiator valves and set heating controls properly. Save Water: Install taps that use less water and check for leaks. Forest School: Plant trees and make outdoor learning spaces. | LR JH | Energy Check Complete a full energy survey within 3 months. Identify at least 5 low-cost energy-saving actions from the audit. Better Lighting All planned LED lighting upgrades installed. Motion and daylight sensors fitted in key areas where budget allows. Fix Leaks All urgent roof leaks repaired within the term. Draught-proofing completed for priority doors and windows. Heating Thermostatic radiator valves fitted in all classrooms. Boiler controls optimized for correct heating zones and schedules. Save Water Install low-flow taps in washrooms and kitchens. Leak detection checks completed termly with no unresolved leaks. Forest School Outdoor learning zone prepared and safe for use. At least 10 new trees planted and maintained within 12 months. | Prioritise actions from audit; pursue grant funding for capital works. | Estates Management; Health & Safety; Capital Funding |
| 3. Behaviour, pupils & leadership | Switch Off Campaign: Remind everyone to turn off lights and devices. End-of-Day Check: Pupils check lights, windows, and waste before leaving. Eco Council: Pupils take roles for Energy, Waste, Nature, and Travel. Track Progress: Pupils measure energy, waste, and wildlife. Rewards: Celebrate classes that make the biggest difference. | ND LR | High checklist compliance across terms. Regular pupil-collected environmental data. Minimum four pupil-led projects per year. Termly Eco updates to governors and in school newsletter. | Embed pupil leadership and reporting into school routines link rewards to measurable outcomes. | Behaviour & Attitudes; Personal Development; Pupil Leadership |
| 4. Curriculum & careers | Climate in Lessons: Learn about the environment in science, geography, art, and more. Outdoor Learning: Use forest school and local green projects. Green Jobs: Meet people who work in eco-friendly jobs. Special Events: Celebrate Earth Day and invite guest speakers. Creative Projects: Make art and stories about helping the planet. | NB ND | Curriculum map completed and implemented. Evidence of taught lessons and pupil outcomes. Pupils can identify local green jobs and explain one climate action. | Align curriculum mapping with assessment cycles; use outdoor zones for experiential learning. | Curriculum; Careers Education; SMSC |
| 5. Food, waste & procurement | Healthy Choices: More plant-based and local food. Check Waste: Count leftover food and try to reduce it. Buy Smart: Choose items that last longer and use less plastic. Recycle More: Better recycling stations and pupil-led campaigns. | KC KA ND JH | Measurable reduction in food waste within one term. Composting or community diversion in place. Sustainable procurement checklist used for all major purchases. Reduction in single-use items. | Start tray waste audits immediately; pilot composting with one year group. | Catering & Nutrition; Procurement; Environmental Sustainability |
| 6. Travel, transport & digital | Walk or Bike: Join walking buses and bike-to-school weeks. Safety First: Learn road safety and bike skills. Staff Travel: Share cars or use public transport. Save Energy on Devices: Turn off computers and use power-saving settings. Online Meetings: Use virtual meetings when possible. | ND JH KA | Maintain/increase percentage of active travel journeys. Secure storage installed. Reduction in single-occupancy staff car use. Power management enabled on devices. | Coordinate active travel weeks with local authority initiatives; include travel data in dashboard. | Travel & Transport; IT Strategy; Staff Wellbeing |
| 7. Community, partnerships & funding | Work Together: Partner with local groups and businesses. Find Funds: Apply for grants and raise money for green projects. Share News: Tell families about progress in newsletters and events. | ND JH | Two active partnerships within 12 months. At least one successful grant or funding application for a key project. Regular community engagement events. | Map potential partners and funding streams within first term. | Community Engagement; External Funding; Parent Partnership |
| 8. Governance, targets & reporting | Clear Goals: Set targets for energy, water, waste, and travel. Track Progress: Use a simple dashboard to show results. Report: Share updates with governors and families every term. | KA JH LR | Policy approved by governors. Termly governor updates provided. Dashboard maintained and reviewed. Annual report published showing progress and next steps. | Use dashboard to inform governor scrutiny and community reporting. | Governance; School Improvement Planning; Accountability |
| Immediate priorities | Complete scheduled LED lighting and ceiling works and install sensors where planned. Repair urgent roof leaks and carry out draught-proofing for priority areas. Train Site Manager in metre reading and basic fault identification. Launch staff CPD and the “Switch Off, Save Energy” campaign; formalise Eco Council pupil roles. | JH LR ND | Energy survey completed and baselines set. Lighting/sensor works progressed. Urgent repairs completed. Site Manager trained. CPD delivered and Eco Council established. | Focus resources on low-cost/high-impact actions while securing funding for capital projects. | Capital Projects; Health & Safety; Staff Development |
| Monitoring & review | Maintain a concise termly dashboard (energy kWh and cost, water use, food waste kg, travel mode share, number of pupil projects) reviewed by SLT and reported to governors. Annual review of targets and actions; update plan and priorities based on survey data, funding opportunities and curriculum needs. | LR JH KA | Dashboard updated termly and reviewed by governors. Annual plan review completed and published. | Integrate monitoring with existing data reporting cycles to governors and stakeholders. | Performance Management; Reporting & Accountability |
| Framework note | This plan supports OFSTED-relevant areas including Curriculum and Teaching, Personal Development and Well-being, Leadership and Governance, Inclusion and Safeguarding where applicable. |  |  | Refer to latest OFSTED framework when preparing governor reports and policy documents. | Ofsted Inspection Framework (relevant areas) |